## Project Charter
PROJECT CHARTER
PROJECT NAME |  |  | DATE |  |  | AREA OF FOCUS
Win Financial Group IT Infrastructure Upgrade |  |  |  | 2023-11-14 | New IT System
| BUSINESS CASE |  |  |  | SPONSOR |  | PROJECT MANAGER
The Win Financial Group (WFG) is a successful financial consulting company experiencing significant growth. With approximately 30 employees and plans to expand to 200 employees within the next year, WFG has leased a 20,000-square-foot building. The current IT infrastructure needs an upgrade to support this growth, and WFG is seeking a partner to acquire and implement a new Network Architecture. |  |  |  |  | Win Financial Group C/O James Deo |  | Kumari Akanksha
[5 empty] | STAKEHOLDERS | PROJECT TEAM
[5 empty] | WFG Management Team | NAME | ROLE
[5 empty] | IT team | Apoorva Dharadhar | Engineering
[5 empty] | Network Administrators | Mohdizhaaramzad Khan | Design/ Testing
[5 empty] | Architect and Engineering Team | Krishnaswathi Peetha | Communications
[5 empty] | Accounting team of WFG | Lakshmialekhya Tatampudi | Finance
Angle Investors of WFG
| GOAL |  |  |  |  | SCOPE
To design and implement a robust IT infrastructure for WFG, supporting the company's growth to 200 employees within the next year. |  |  |  |  | IN SCOPE |  | OUT OF SCOPE
[5 empty] | Design |  | Labour cost
[5 empty] | Wired Edge Network |  | MS Applications
MEASURABLE TARGETS |  |  |  |  | Core Network |  | cubicles
Creation of physical layer |  | Tuesday, December 16, 2023 |  |  | WiFi Edge Network |  | patch cables
wireless Network design |  | Tuesday, January 12, 2024 |  |  | Local Active Directory (AD) Server |  | Furniture
Ad Server Instalation / Setup |  | Tuesday, Feb 6, 2024 |  |  | Local File Share Server |  | Firewall
File Share Server / Setup |  | Tuesday, March 25, 2024 |  |  | Cloud-based Active Directory (AD) Server |  | Anti virus
Fault-tolerant cloud-based Active Directory server |  | Tuesday, April 3, 2024 |  |  | Software Licensing
Project Turnover |  | Friday, May 3, 2021 |  |  | Subscriptions
FLEXIBILITY MATRIX |  |  |  |  | Switces
SCOPE MEDIUM FLEXIBILITY |  |  |  |  | Routers
SCHEDULE HIGH FLEXIBILITY |  |  |  |  | Computers
COST LOW FLEXIBILITY |  |  |  |  | Ip phones
| SUCCESS CRITERIA |  |  |  | ASSUMPTIONAS & CONSTRAINTS
1. Implementation of the entire IT infrastructure within the specified timeline |  |  |  |  | 1. Adequate power and network infrastructure in the leased building.
2. No disruptions to daily operations during the implementation phase. |  |  |  |  | 2. Full cooperation from WFG's IT team during the implementation phase.
3. Scalability to accommodate the planned growth to 200 employees. |  |  |  |  | 3. Project is fully funded.
4. Fault-tolerant and redundant systems for critical services. |  |  |  |  | 4. There is separate rooms for MDF and IDF
5. Seamless connectivity for all end-users
| PROJECT MANAGEMENT APPROACH |  |  |  | RISK
The project will follow a phased approach, similar to the Waterfall project management model. Each component of the IT infrastructure will be implemented sequentially, ensuring proper integration and functionality. |  |  |  |  | RISK LEVEL | DESCRIPTION
[5 empty] | HIGH | Potential delays due to unforeseen technical challenges
[5 empty] | HIGH | Sudden increase in project scope
[5 empty] | MEDIUM | Integration challenges between local and cloud servers
All necessary documentation will be submitted to Win Financial Group in accordance with plan and schedule. |  |  |  |  | LOW | Third-party vendor delays
[5 empty] | LOW | Avability of selected network devices
| SIGNATURES |  |  |  | RISK PLANNING
SPONSOR'S SIGNATURE |  |  |  |  | Always have some buffer time for unseen issues
Printed Name: James Deo, Contracting Officer - 108th Neil Hills |  |  |  |  | Regular communication with stakeholders
Signature: |  |  |  |  | Referring technical documentations
Date: 11-14-2023 |  |  |  |  | Scope, cost, and schedule uncertainty;
MANAGER'S SIGNATURE |  |  |  |  | FINANCIALS
Printed Name: Kumari Akanksha - Project Manager |  |  |  |  | Hardware cost : | $ 35,000
Signature: |  |  |  |  | Software Licensing cost : | $ 12,000
Date: |  |  |  |  | Cloud Services Fees | $ 1,65 0
[5 empty] | Labour Cost | $ 47, 000

## Risk Register
RISK REGISTER
Create Date | Category | Description | Likelihood | Impact | Impact Cost | Schedule Impact (Days) |  | Probability |  | Cost EMV | Schedule EV |  | Updated By | Date Updated | Risk ID | Occurance of Risk | Outcome of Risk | Detection of Risk | Risk Score | RPN
11.14.23 | Scope | Scope Creep | Low | Increased costs and Timeline extensions | 50000 |  | 23 |  | 1% | 500 | 0.23 |  | Alekhya | 2023-06-11 | 1 | 7 | 7(Schedule) | 5 | 49 | 245 | Value | Occurance of Risk | Outcome of Risk | Detection of Risk
11.14.23 | Financial | Budget Constraints | High | Increased Costs | 20000 |  | 0 |  | 30% | 6000 | 0 |  | Swathi | 2023-06-11 | 2 | 4 | 9 (Cost) | 4 | 36 | 144 | 10 | High | Project Shutdown | Hard to detect
11.15.23 | Technology | Technology Obsolescence | Low | Technology may become outdated | 5000 |  | 10 |  | 10% | 500 | 1 |  | Aporva | 2023-06-11 | 3 | 6 | 7 (Performance) | 7 | 42 | 294 | 9 | Medium | Temporary project shutdown | Can be detected
11.15.23 | Security | Data Security Concerns | Low | Data breaches and other cybersecurity threats | 15000 |  | 0 |  | 5% | 750 | 0 |  | Akansha | 2023-06-11 | 4 | 2 | 9 (Scope) | 4 | 18 | 72 | 8 | Low | Customer Dissatisfaction | Low possibility
11.16.23 | Management | Project Management Mistakes | High | Delayed schedule, Increased Costs | 15000 |  | 15 |  | 30% | 4500 | 4.5 |  | Izhaar Khan | 2023-06-11 | 5 | 2 | 7(Scope) | 7 | 14 | 98 | 7 | Rare | Scope change | Can be detected
11.16.23 | Management | User Training Issue | Low | Poor training resulting in low user uptake | 5000 |  | 10 |  | 20% | 1000 | 2 |  | Alekhya | 2023-06-11 | 6 | 1 | 6 (Performance) | 8 | 6 | 48 | 6 | Frequent | Project cost increase | Remote possibility of detection
11.17.23 | Timeline and Schedule | Delays in project timelines | Medium | dissatisfaction from the client and delayed business benefits | 5000 |  | 8 |  | 15% | 750 | 1.2 |  | Alekhya | 13.11.2023 | 7 | 6 | 8 (Performance) | 9 | 48 | 432
11.15.23 | Privacy | Security threats if not handled properly | Low | reputational damage | 10000 |  | 0 |  | 5% | 500 | 0 |  | Swathi | 13.11.2023 | 8 | 2 | 9 (Scope) | 3 | 18 | 54
11.15.23 | Integration and Compatibility | Compatibility issues when integrating | Medium | Data loss | 10000 |  | 15 |  | 23% | 2300 | 3.45 |  | Aporva | 13.11.2023 | 9 | 3 | 8 (Scope) | 7 | 24 | 168
11.14.23 | Vendor Management | vendors experience issues | Low | Increased project costs | 20000 |  | 0 |  | 25% | 5000 | 0 |  | Akansha | 13.11.2023 | 10 | 5 | 8 (Schedule) | 3 | 40 | 120
11.16.23 | Regulatory Compliance | legal consequences | Low | Fines and legal actions | 15000 |  |  |  | 4% | 600 | 0 |  | Izhaar Khan | 13.11.2023 | 11 | 1 | 10 (Scope) | 2 | 10 | 20
11.15.23 | Communication | Inadequate communication | Low | Rework and increased costs | 5000 |  | 30 |  | 16% | 800 | 4.8 |  | Alekhya | 13.11.2023 | 12 | 7 | 6 (Cost) | 1 | 42 | 42
175000 | [6 empty] | TOTAL WEIGHTED |  |  | 23200 |  | 17.18
|  |  | Risk ID | RPN
|  |  | 1 | 245
|  |  | 2 | 144
|  |  | 3 | 294
|  |  | 4 | 72
|  |  | 5 | 98
|  |  | 6 | 48
|  |  | 7 | 432
|  |  | 8 | 54
|  |  | 9 | 168
|  |  | 10 | 120
|  |  | 11 | 20
|  |  | 12 | 42
|  |  | Risk ID | Risk Score
|  |  | 1 | 0
|  |  | 2 | 36
|  |  | 3 | 42
|  |  | 4 | 18
|  |  | 5 | 14
|  |  | 6 | 6
|  |  | 7 | 48
|  |  | 8 | 18
|  |  | 9 | 24
|  |  | 10 | 40
|  |  | 11 | 10
|  |  | 12 | 42

## Issues Log
ISSUES TRACKER
Issue ID# | Issue Owner | Issue Title | Issue Description | Issue Category | Issue Type | Priority | Issue Status | Date Created | Date Resolution Required | Date of Actual Resolution
10001 Apoorva Dharadhar Memory slot mismatch Memory configurations not satisfying the requirements due to mismatch Hardware Memory Configuration Moderate | [6 empty] | Resolved | 11-01-2024 11-05-2023 11-07-2023
10002 Krishnaswathi P. Insufficient PoE Ports on switches Deployment of PoE devices such as phones affected by limited no. of PoE ports. Infrastructure Resource Constraint Moderate | [6 empty] | Resolved | 11-29-2023 12-04-2023 12-05-2023
10003 Izhaar Khan Insufficient available IPs Challenges in accomodating the additional devices Network Resource Exhaustion Resource Management Moderate | [6 empty] | Pending | 11-28-2023 12-08-2023
10004 Lakshmi Alekhya T. Compliance to Microsoft Licensing Performance and operational issues due to licensing non-compliance License Compliance Licensing Violation High | [6 empty] | Resolved | 12-01-2023 12-02-2023 12-01-2023
10005 Krishnaswathi P. No. of APs out of budget No. of Aps exceeding allocaed budget, resulting in financial constraints Budget Contraint Cost Overrun Moderate | [6 empty] | Resolved | 12-08-2023 12-12-2023 12-11-2023
10006 Izhaar Khan NIC Firmware Incompatibility Connectivity Issue caused because of the incompatibility of NIC. Hardware Firmware Incompatibility Moderate | [6 empty] | Pending | 12-08-2023 12-13-2023
10007 Apoorva Dharadhar Mismatched Configurations of VLANs Failed communication between network endpoints due to mismatched VLANs. Configuration Network Configuration Moderate | [6 empty] | Resolved | 12-18-2023 12-22-2023 12-21-2023
10008 Izhaar Khan Heating and Cooling Equipment Failure Overheating poses threat to equipment failure. Facilities Equipment Failure High | [6 empty] | In Progress | 12-26-2023 12-27-2023
10009 Apoorva Dharadhar Edge & core servers incompatible Connectivity and Performance problems due to imcompatibility Infrastructure Server Compatibility Medium | [6 empty] | Resolved | 12-26-2023 12-29-2023 12-28-2023
10010 Krishnaswathi P. Access Point placement un-optimized Wifi coverage gaps created, resulting in poor connectivity in the gaps. Infrastructure Wireless Network Optimization Low | [6 empty] | Pending | 02-02-2024 02-13-2024

## Communication Plan
COMMUNICATIONS MANAGEMENT PLAN
Artifact | Purpose | Frequency | Medium | Attendees | Host
Preparatory Phase Meeting | To discuss project overview including the purpose, requirements, scope, objectives, etc. | Beginning of Project | Live Meeting | Management Team | Project Manager
Project Launch Meeting | To define roles and responsibilities of team members, establish schedules, discuss critical path and dependencies. | Beginning of Project | Live Meeting | Team lead, all team members | Project Manager
Weekly Progress Meeting | Track the status of the project, discuss any issues or concerns, outline the tasks planned for upcoming week. | Weekly | Virtual meeting | All team members | Team Lead
Request for Information (RFI) | To request any clarifications related to project scope, specifications or expectations | As Needed | Email | Management Team, Interested team members | Project Manager
Document review session | To assess documents related to project, ensure that the documents are accurate and align with project specifications | Bi-weekly | Virtual meeting | All team members | Team Lead
Project Status Meeting | To discuss status, progress and upcoming milestones of the project | Montly | Virtual meeting | Team lead, all team members | Project Manager
Risk Communication Meeting | To communicate project risks and mitigation plans | As Needed | virtual meeting | Team lead | Project Manager
Change Order Request | To discuss changes to the project scope | As Needed | Email or virtual meeting | Management Team, Team lead | Project Manager
Outage Requests | To notify regarding possible outrage | As Needed | Email | All team members | Project Manager
Training and Awareness | Communication related to training and awareness for the team members | As Needed | Virtual meeting | Team members | Team Lead
Project Documentation | To review paperwork or electronic files related to the project | Periodically | Paper work or Email | Management team, Team lead | Project Manager
Closure and Lessons learned | To discuss project closure, including celebrating successes and gathering lessons learned. | End of the project | Live meeting | Management Team, All team members | Project Manager

## Stakeholder Register
STAKEHOLDER MANAGEMENT PLAN: Win Financial Group IT Infrastructure Upgrade
Beginning Date 11/16/2023 End Date 2/12/2024 Duration: 90 Days Project Manager: Kumari Akanksha
Stakeholder | Role | Influence | Risk Tolerance | Desired Outcome | Project Impact
WFG IT Team | Implementation | High | Moderate | Align infrastructure with business needs | Responsible for troubleshooting, technical aspects and ensuring functionality
WFG Network Adminisrators | Security | High | Low | Secured Network | Installing anti virus and firewalls to make sure the network is secured and there are no data breaches
WFG Accounting Team | Budgeting | High | Low | Cost-effective Infrastructure | Making sure there everything is done within the budgetng constraints
WFG Mamagement Team | Direction | Moderate | Moderate | Integration of IT Infrastructure | Determining project direction and resource allocation
Architechet and Engineering Team | Stability | High | Low | Well -Designed Network Infrastructure | Design both physical and network layer according to the business requirements
Angel Investors of WFG | Finanace | Low | High | Funds for resources | Making sure there is flow of funds durin the course of the project
CISCIO | Hardware | High | Low | High-quality hardware | Provideinf with high quality hardware that meets the need of all the specifications mentioned in a timely manner
Microsoft | Software licensing | Moderate | Moderate | Subscriptions for softwares | Proving all the necessary sofwares and user licensing needed
Amazon Web Services | Cloud | High | Low | Cloud Server Security | Providing a secure clod server as per the specifications
WFG Employees | End User | Moderate | Low | Adapt new Infrastructure | Cooperating and adapting the new infrastructure to ensure smooth workflow

## Change Management Plan
CHANGE MANAGEMENT PLAN
ID | Description | Priority | Requestor | Date requested | Date Assigned | Approver | Status | Date of Decision | Scope Impact | Time impact | Cost Impact
1 | Identifying Milestone Increase 24 hrs labor (1 day Delay). | High | Apoorva | 2023-11-25 | 2023-11-24 | Akanksha | Approved | 2023-11-21 | Additional Labour | 24 hrs | $ 960.00
2 | Firewall Integration Increase in 16 hrs labour (1 day delay) | Medium | Apoorva | 2023-12-08 | 2023-12-08 | Akanksha | Aprroved | 2023-12-06 | Additional Labour | 16 hrs | $ 640
3 | Access Point Model Selection Two more Access points needed (cost increased) | High | Apoorva | 2023-12-12 | 2023-12-15 | Akanksha | Approved | 2023-12-14 | Additional Cost | 0 | $ 3096
4 | Server Functionality Testing Technical issue (1 day Delay) | Medium | ,Krishnaswathi Peetha | 2024-02-07 | 2024-02-07 |  | Pending |  | Additional Labour | 16 | $ 640

## Project Budget
BUDGET BY PHASE
Project: | Win Financial Group IT Infrastructure Upgrade |  |  | Project Sponsor: Win Financial Group C/O James Deo
Project Manager: | Kumari Akanksha |  |  | Last Updated: 05/12/2023
COSTS
| BASELINE 1 |  |  | BASELINE 2 |  |  |  | BASELINE 3
PHASE | COST | CRITICAL PATH DURATION (DAYS) |  | COST |  | CRITICAL PATH DURATION (DAYS) |  | COST | CRITICAL PATH DURATION (DAYS)
Project Planning
Define Project Scope | 1904 | 3.25 |  | 1904 |  | 3.25 |  | $1,904.00 | 3.25
Develop Project Schedule | 2480 | 3 |  | 3440 |  | 4 |  | $3,440.00 | 4
Network Infrastructure Design
Edge Network Design | 28432 | 2.75 |  | 28432 |  | 2.75 |  | $28,432.00 | 2.75
Core Network Design | 16569 | 5.25 |  | 17209 |  | 6.25 |  | $17,209.00 | 6.25
Wi-Fi Network Implementation
Access Point Procurement | 33200 | 5 |  | 33200 |  | 5 |  | $36,296.00 | 5
SSID Configuration | 640 | 2 |  | 640 |  | 2 |  | $640.00 | 2
Server Procurement and Setup
Local AD Server | 8855 | 5 |  | 8855 |  | 5 |  | $8,855.00 | 5
File Server | 8695 | 4.5 |  | 8695 |  | 4.5 |  | $8,695.00 | 4.5
Cloud Ad Server | 1326.21 | 2 |  | 1326.21 |  | 2 |  | $1,326.21 | 2
Integration and Testing
Network Integration | 2400 |  | 5.5 | 2400 |  | 5.5 |  | $2,400.00 | 5.5
Server Setup and Testing | 3680 |  | 11.5 | 3680 |  | 11.5 |  | $3,680.00 | 11.5
Documentation and Training
Network Documentation | 3080 |  | 3.5 | 3080 |  | 3.5 |  | $3,080.00 | 3.5
User Traning | 10048 |  | 11 | 10048 |  | 11 |  | $10,048.00 | 11
Project Closure
Final Testing and Quality Assurance | 2560 |  | 4 | 2560 |  | 4 |  | $3,200.00 | 5
Lessons Learned and Project Report | 4480 |  | 5 | 4480 |  | 5 |  | $4,480.00 | 5
SUBTOTAL | 128349.21 | 73.25 |  | 129949.21 |  | 75.25 |  | 133685.21 | 76.25
Contingency | 23200 | 17 |  | 23200 |  | 17 |  | 23200 | 17
TOTAL Costs | 151549.21 |  | 90.25 |  | 153149.21 |  | 92.25 | 156885.21 | 93.25