## Status Report 1
STATUS REPORT
| Project: Win Financial Group IT Infrastructure Upgrade |  | Updated: 12-12-2023
Baseline # |  | 3
Project % Complete |  | 51.66%
Overall Project Health (G/Y/R) |  | G
Variance Report |  | The project is slightly delayed. The project is slightly over budgut.
Earned Value Management Metrics
Earned Value (EV) |  | 66305
Actual Cost (AC) |  | 69453
Scheduled Performance Index (SPI) |  | 0.9899
Cost Performance Index (CPI) |  | 0.95467
Project Cost by Phase |  | Budgeted | Actual to Date | % Complete | PV | EV
Project Planning |  | 4384 | 5344 | 100% | 4384 | 4384
Network Infrastructure Design |  | 45001 | 45641 | 100% | 45001 | 45001
Wi-Fi Network Implementation |  | 33840 | 18468 | 50% | 17596.8 | 16920
Server Procurement and Setup |  | 18876.21 |  | 0% | 0 | 0
Integration and Testing |  | 6080 |  | 0% | 0 | 0
Documentation and Training |  | 13128 |  | 0% | 0 | 0
Project Closer |  | 7040 |  |  |  | 0
|  | 128349.21 | 69453 |  | 66981.8 | 66305
Project Reserves Breakdown |  | Budget / Planned | Actual to Date
Contingency Reserve |  | 23200 | 3000

## Status Report 2
STATUS REPORT
| Project: Win Financial Group IT Infrastructure Upgrade |  | Updated: 12-01-2024
Baseline # |  | 3
Project % Complete |  | 84.05%
Overall Project Health (G/Y/R) |  | G
Variance Report |  | The project is on time. The project is slightly over budget.
Earned Value Management Metrics
Earned Value (EV) |  | 107877.21
Actual Cost (AC) |  | 112877.21
Scheduled Performance Index (SPI) |  | 0.99719
Cost Performance Index (CPI) |  | 0.9557
Project Cost by Phase |  | Budgeted | Actual to Date | % Complete | PV | EV
Project Planning |  | 4384 | 5344 | 100% | 4384 | 4384
Network Infrastructure Design |  | 45001 | 45641 | 100% | 45001 | 45001
Wi-Fi Network Implementation |  | 33840 | 36936 | 100% | 33840 | 33840
Server Procurement and Setup |  | 18876.21 | 18876.21 | 100% | 18876.21 | 18876.21
Integration and Testing |  | 6080 | 6080 | 95% | 6080 | 5776
Documentation and Training |  | 13128 |  | 0% | 0 | 0
Project Closer |  | 7040 |  | 0% | 0 | 0
|  | 128349.21 | 112877.21 |  | 108181.21 | 107877.21
Project Reserves Breakdown |  | Budget / Planned | Actual to Date
Contingency Reserve |  | 23200 | 3000